## Master Summary
TREZO — COMPLETE DEVELOPMENT RECORD
From the first Woven Basket precursor (June 2025) through the live Trezo platform. Good-faith business record; every figure carries its evidence tier.
INPUTS (blue, yellow = edit)
Full-arc start — earliest substantiated precursor (Woven Basket, Nokia credit-collar work) |  | 2025-06-11
Report as of |  | 2026-08-19
THE FULL ARC
Elapsed calendar days |  | 434
Inclusive calendar days |  | 435
Full weeks |  | 62
Remaining days |  | 0
Approximate months (30.4375-day avg) |  | 14.2587
Weekdays / weekend days in span |  | 311 / 124 | Calendar composition to 2026-08-19 (computed; recompute if as-of changes). Not proof of days worked.
THREE ERAS, THREE KINDS OF EVIDENCE
Era | Period | Business activity | Hours | Evidence tier
1 — Strategy R&D (Woven Basket) | 2025-06-11 → 2026-05-17 | R&D, strategy development, IP development: credit-collar precursor → $2k/month income system → seven-layer Woven Basket v1-5 (proprietary IP) | Not recoverable | Reconstructed from recovered conversation records; Medium/Low confidence
2 — Platform foundation | 2026-05-15 → 2026-06-01 | System development begins: first Trezo folder (May 15, 15:43:15), environment and design work predating version control. Note: overlaps Era 1 — Woven Basket v1-5 (May 17) was finalized as platform work began. | Not recoverable | Folder timestamp (high); period contents user-recalled
3 — Platform build (Trezo) | 2026-06-01 → present | System development, revision, documentation: 198 commits, 22 agents, 3 books, ops hardening, profit-protection system | ≥ 218.3 h (floor) | Git commit history (high); hours are a floor — see Method
KEY CONCLUSION
The available record supports a continuous development arc from at least June 11, 2025 through the present: strategy R&D culminating in Woven Basket v1-5, flowing directly into the Trezo platform that implements it. Active-work hours are defensible only for Era 3 (git-evidenced floor, currently 218.3 h plus manual additions). Eras 1–2 are spans with substantiated milestones, not hour claims — original chat or file-version timestamps can be added later to upgrade them.

## Unified Timeline
UNIFIED DEVELOPMENT TIMELINE
Every substantiated milestone across both records, in order. Fill color = evidence tier.
Date | Era | Phase | What happened | Evidence / source | Confidence
2025-06-11 | 1 | Foundation | Nokia recurring-premium / portfolio-protection precursor work begins. | Recovered ChatGPT record (turn 6caf0a78…) | Medium
2025-06-16 | 1 | Foundation | Credit-collar structure: shares, short calls, long puts, roll/management logic. | Recovered ChatGPT record (turn 6caf0a78…) | Medium
2025-09-24 | 1 | Income system | Stock/options system targeting ~$2,000/month — ancestor of the income architecture. | Recovered ChatGPT record (turn 6caf0a78…) | Medium
2026-01→02 | 1 | Integration | Extended work and several documents recalled; artifacts not recovered. | User recollection only | Low
2026-03 | 1 | Integration | Precursor concepts leading into Woven Basket reported in earlier review. | Assistant statement (turn b21e376d…) | Low
2026-05-13 | 1 | Formalization | The Woven Basket Investment Strategy named: seven interconnected layers, cross-layer protection, cash-flow waterfall. | Recovered ChatGPT record (turns b21e376d…, 4d170423…) | Medium
2026-05-15 | 2 | Foundation | First Trezo folder created, 3:43:15 PM — platform work begins. | Folder creation timestamp | High
2026-05-17 | 1 | Culmination | Woven Basket v1-5 — architecture identified as proprietary IP. Strategy finalized as platform work began. | Recovered ChatGPT record (turn 4d170423…) | Medium
2026-06-01 | 3 | Baseline | First commit: paper page recovered, capital pressure shipped. Version control begins. | Git commit | High
2026-06-12 | 3 | Hardening | Marathon audit: 32 fixes — crypto exits, Wheel universe, position trimming. | Git commits | High
2026-06-13 | 3 | Crypto lane | Crypto Part 1: classification fixed, HODL accumulate-and-hold added. | Git commits (10) | High
2026-07-02 | 3 | Realism | ATR-capped realistic targets; crypto revival (dead-SCALP bug, live volume). | Git commits (12) | High
2026-07-11 | 3 | One scale | TCS unified 0–100 platform-wide. | Git commit | High
2026-07-15 | 3 | Protection | Leg-resync hardened: broker-truth quantity, protection-first stop fallback. | Git commits (10) | High
2026-07-27 | 3 | Learning | Agents gain a voice: evidence-backed rule-change proposals. | Git commits (6) | High
2026-07-28 | 3 | Security | Security sweep: engine unpublished from network, loopback write-guard. | Git commits (5) | High
2026-08-05 | 3 | Hardening | Market-shut harvest bug + failed leg check read as all-clear — 22-commit day. | Git commits (22) | High
2026-08-09 | 3 | Multi-book | Owner/account split: 5k, 25k, 75k books with per-book credentials. | Git commits (5) | High
2026-08-18 | 3 | Venue safety | Stops and take-profits rest AT the broker, surviving engine outages. | Git commits (23) | High
2026-08-19 | 3 | Turnaround | Profit ladder retuned from 30-day evidence; single-engine enforcement; DCA bounce gate; ~$1,900 locked in first 15 minutes; 5k book recrosses $5,000. | Git commits (11) + broker screenshots | High
Green = substantiated (recovered record, timestamp, or git). Gold = inferred / user-recalled — kept, labeled, and excluded from any hour total.

## Work Log (Trezo)
ERA 3 WORK LOG — GIT-DERIVED + MANUAL
Rows marked git regenerate from commit history (tools/worklog.py). Yellow manual rows are yours.
Date | Month | Commits | First | Last | Hours | Source | What shipped / notes
2026-06-01 | 2026-06 | 1 | 18:45 | 18:45 | 1 | git | Trezo baseline 2026-06-01 - paper page recovered, capital pressure shipped
2026-06-03 | 2026-06 | 1 | 20:12 | 20:12 | 1 | git | Trezo snapshot 2026-06-03 - all green: 22 agents, sliding-scale giveback, OpsWatchdog, auto-reconcile
2026-06-04 | 2026-06 | 1 | 11:54 | 11:54 | 1 | git | Trezo snapshot 2026-06-04 - all green: 22 agents, sliding-scale giveback, OpsWatchdog, auto-reconcile
2026-06-12 | 2026-06 | 3 | 02:29 | 22:07 | 19.63 | git | 2026-06-11/12 marathon audit: 32 fixes - crypto exits, Wheel full-market universe, trim_positions
2026-06-13 | 2026-06 | 10 | 04:13 | 18:30 | 14.28 | git | Crypto Part 1: fix crypto classification (ISO coins -> modeled engine), add HODL accumulate-and-hold
2026-06-16 | 2026-06 | 1 | 17:47 | 17:47 | 1 | git | 6/16 bug-fix + self-healing integrity sweep
2026-06-17 | 2026-06 | 2 | 02:08 | 08:25 | 6.28 | git | 6/16 learning loop: outcome-weighted strategy selection + macro fall-through
2026-06-19 | 2026-06 | 9 | 05:17 | 17:10 | 11.88 | git | Paper page: positions/trades up top; account-size testing to Strategy Lab
2026-06-23 | 2026-06 | 2 | 13:47 | 14:18 | 1 | git | Trading: integrity flags - classify positions Live/Modeled/Unconfirmed vs Alpaca
2026-06-26 | 2026-06 | 3 | 18:32 | 19:22 | 1 | git | Agents: route crypto + options exits through the shared capability library
2026-06-29 | 2026-06 | 3 | 13:55 | 16:18 | 2.38 | git | Trading page: show why each position is held + its path to profit
2026-07-01 | 2026-07 | 2 | 22:25 | 22:39 | 1 | git | Visibility pack: activity log wired into vetoes, approvals, pocket skips, submits, broker rejects
2026-07-02 | 2026-07 | 12 | 05:47 | 14:45 | 8.97 | git | Realistic ATR-capped targets, crypto revival (dead-SCALP units bug + volume bar + CoinGecko)
2026-07-06 | 2026-07 | 3 | 13:40 | 14:17 | 1 | git | R:R-consistent stops when realism caps targets (unblocks sizing-rejected approvals)
2026-07-07 | 2026-07 | 2 | 11:26 | 12:12 | 1 | git | Post-wipe armor: bracket price clamps + notional/BP cap (kills the 422/403 reject storm)
2026-07-08 | 2026-07 | 1 | 17:06 | 17:06 | 1 | git | Posture-scaled wheel limits (growth: 1 CSP, 21 DTE, 25% collateral), CSP buy-backs queued
2026-07-09 | 2026-07 | 3 | 10:57 | 11:08 | 1 | git | Self-calibrating targets: median achieved peak move per strategy caps new targets
2026-07-11 | 2026-07 | 1 | 16:34 | 16:34 | 1 | git | ONE SCALE: TCS 0-100 platform-wide (scorer, every floor, bumps, confidence, scope rows)
2026-07-13 | 2026-07 | 6 | 12:54 | 14:13 | 1.32 | git | PROJECT_STATUS 2026-07-13 (atom hero, STMS 7A-4P, Sector Compass, wider desks, ETH orphan)
2026-07-14 | 2026-07 | 13 | 08:36 | 15:07 | 6.52 | git | Strategy Lab: portfolio-driven pattern charts, market/industry scan with save-as-watchlist
2026-07-15 | 2026-07 | 10 | 05:35 | 17:23 | 11.8 | git | Leg-resync hardened: broker-truth quantity + protection-first stop fallback (PYPL partial fill)
2026-07-16 | 2026-07 | 5 | 08:07 | 19:31 | 11.4 | git | Harvest one-shot guard re-arms daily: an expired unfilled buy-back retries tomorrow
2026-07-20 | 2026-07 | 3 | 10:46 | 10:51 | 1 | git | Paper page: forex cards get real numbers (Kraken live spot, Forex badge, forex_swing copy)
2026-07-22 | 2026-07 | 2 | 17:02 | 17:08 | 1 | git | Stop paying for dead symbols: no-data rest list + warrant filter + quiet yfinance
2026-07-23 | 2026-07 | 4 | 04:00 | 14:46 | 10.77 | git | Crypto desk unblocked: coverage floor reaches the scanner, BTC joins the universe
2026-07-24 | 2026-07 | 2 | 11:24 | 11:33 | 1 | git | HOTFIX: AlpacaAccount dataclass field order (non-default cash after default)
2026-07-27 | 2026-07 | 6 | 11:24 | 18:21 | 6.95 | git | The agents get a voice: evidence-backed rule-change proposals + library that returns craft
2026-07-28 | 2026-07 | 5 | 16:24 | 21:40 | 5.27 | git | Security sweep: service installer no longer publishes the trading engine + loopback write-guard
2026-08-03 | 2026-08 | 5 | 20:54 | 22:36 | 1.7 | git | Remove the temporary tsconfig.check.json (typecheck scratch file, committed by accident)
2026-08-05 | 2026-08 | 22 | 03:11 | 23:17 | 20.1 | git | fix: step profit harvest ran while the market was shut, and a failed leg check read as all-clear
2026-08-06 | 2026-08 | 2 | 00:03 | 00:05 | 1 | git | hrp: allocation across lanes, and a bugfix it exposed (phase 6, part 1)
2026-08-07 | 2026-08 | 1 | 14:30 | 14:30 | 1 | git | fix: scalps had no exit path, and the kill-switch was 33x too tight
2026-08-09 | 2026-08 | 5 | 10:55 | 14:02 | 3.12 | git | multi-account: owner/account split, per-book credentials, dividend schedule
2026-08-10 | 2026-08 | 1 | 14:12 | 14:12 | 1 | git | scan pool: rank actives by trade count, not share volume
2026-08-11 | 2026-08 | 5 | 09:53 | 14:56 | 5.05 | git | dividends: 15k is the 75k sleeve's INITIAL DEPLOYMENT, not a pocket pin
2026-08-12 | 2026-08 | 3 | 13:28 | 20:28 | 7 | git | requirements: add mem0ai - hand-installed on the PC, so the server venv build failed silently
2026-08-17 | 2026-08 | 4 | 09:41 | 19:25 | 9.73 | git | fix: ops relay drains EVERY tick, not once a day - first wiring landed inside the janitor's job
2026-08-18 | 2026-08 | 23 | 10:56 | 23:58 | 13.03 | git | Rest the crypto take-profit at the venue, and release it before selling
2026-08-19 | 2026-08 | 11 | 00:03 | 23:10 | 23.12 | git | Profit ladder retuned + rival-engine cleanup + DCA bounce gate + work log tooling
MANUAL ENTRIES — pre-repo days, research, SQL, server ops, calls
2026-05-16 | 2026-05 |  | 09:00 | 13:30 | 4.5 | example | EXAMPLE ROW — platform planning, no commits. Delete or overwrite.
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
manual
TOTAL RECORDED HOURS (Era 3) |  |  |  |  | 218.3

## Monthly (Trezo)
ERA 3 MONTHLY SUBTOTALS
Month | Days recorded | Commits | Hours | % of hours
2026-05 | 0 | 0 | 0 | 0%
2026-06 | 11 | 36 | 60.45 | 27.69%
2026-07 | 17 | 80 | 72 | 32.98%
2026-08 | 11 | 82 | 85.85 | 39.33%
TOTAL | 39 | 198 | 218.3 | 100%
2026-05 = 0 until pre-repo work is added as manual rows on the Work Log tab.

## WB Timeline
ERA 1 — WOVEN BASKET DEVELOPMENT TIMELINE (imported)
Imported unchanged from Woven_Basket_Strategy_Development_Timeline.xlsx. Blank durations mean the source does not support an exact interval — hours are NOT RECOVERABLE, not zero.
Start | End | Days | Document / version | Work performed | Evidence | Confidence | Classification
2025-06-11 | 2025-06-16 | 5 | Nokia recurring-premium / protection precursor | Recurring-premium and portfolio-protection concepts; by June 16: shares, short calls, long puts, roll/management logic. | ChatGPT task record; turn 6caf0a78… | Medium | VERIFIED milestone; hours unknown
2025-09-24 | 2025-09-24 | 0 | $2,000/month stock-options system precursor | Stock/options system targeting ~$2,000/month — ancestor of the income architecture. | ChatGPT task record; turn 6caf0a78… | Medium | VERIFIED milestone; hours unknown
2026-01-01 | 2026-02-28 | 58 | Unrecovered January–February precursor documents | Extended work and several documents recalled; exact dates, versions and durations not recovered. | User recollection; no artifact recovered | Low | INFERRED / USER-RECALLED
2026-03-01 | 2026-03-31 | 30 | Unnamed Woven Basket precursor concepts | March evidence of concepts leading into Woven Basket reported; conversation/date not preserved. | Assistant statement; turn b21e376d… | Low | INFERRED milestone; hours unknown
2026-05-13 | 2026-05-13 | 0 | The Woven Basket Investment Strategy (earliest named; v1-2 or earlier) | Named strategy: seven interconnected layers, cross-layer protection logic, cash-flow waterfall. | ChatGPT task record; turns b21e376d…, 4d170423… | Medium | VERIFIED milestone; hours unknown
2026-05-17 | 2026-05-17 | 0 | Woven Basket Strategy v1-5 (latest recovered) | Refined architecture identified as proprietary IP. Culmination point of the reconstruction; finality not independently proven. | ChatGPT task record; turns 4d170423…, b21e376d… | Medium | VERIFIED milestone; hours unknown
Evidence register (E-01…E-05), calculation rules and audit notes remain in the companion file Woven_Basket_Strategy_Development_Timeline.xlsx, which stays the source of record for Era 1.

## Method
METHOD, EVIDENCE TIERS & LIMITS
Purpose
A single good-faith business record of the development of the Woven Basket strategy and the Trezo platform that implements it, suitable for personal accountability records. It shows continuous work from June 2025 to the present while never claiming more precision than the evidence supports.
Evidence tiers
HIGH: git commit history and filesystem timestamps — independently verifiable. MEDIUM: recovered conversation records naming dates and artifacts. LOW: user recollection without a recovered artifact — kept for context, never counted in hours.
Hours policy
Hours appear ONLY where evidence supports them. Era 3's total is a floor derived from commit-day spans (tools/worklog.py in the repo regenerates it). Eras 1–2 say 'not recoverable' rather than reporting a false zero or an invented estimate. Original chat timestamps or document version histories, if recovered later, can be added as manual rows to upgrade the record.
Continuity
The two records overlap by design: the first Trezo folder (2026-05-15 15:43:15) predates Woven Basket v1-5 (2026-05-17). The strategy was being finalized as its implementation began — Era 1 flows into Era 3 without a gap.
Classification of activity
Era 1: research & development, strategy development, IP development. Era 2: system development (foundation). Era 3: system development, revision, documentation — per-day detail on the Work Log tab.
If this is used for business records
This workbook provides dates, evidence and hour floors. Whether any of it is claimable as business time or expense is a question for a CPA.